## Sheet1
FRONT-END DESIGN in React
Task | Start Date | End Date | Total Days | Status
Navbar, Footer, How it work, Pricing | 2026-02-20 | 2026-02-20 | 1 | Complete
Landing Page, Consultant Page | 2026-02-21 | 2026-02-21 | 1 | Complete
Full Website+ Responsiveness | 2026-02-22 | 2026-02-22 | 1 | InProcess
|  | Move Toward Dashbaord |  | Pending
SideBar, setup All pages | 2026-02-23 | 2026-02-23 | 1 | Pending
Project Mangement | 2026-02-24 | 2026-02-24 | 1 | Pending
Ai Matching | 2026-02-25 | 2026-02-25 | 1 | Pending
Verfication | 2026-02-26 | 2026-02-26 | 1 | Pending
Settings | 2026-02-27 | 2026-02-27 | 1 | Pending
Dashboard Design | 2026-02-28 | 2026-03-01 | 2 | Pending
Full frontend Project | 2026-03-02 | 2026-03-02 | 1 | Pending
Total Days | 2026-02-20 | 2026-03-03 | 12 days